## Sheet1
Product Backlog Story | Story Points | Assigned To | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | General Notes
As a client, I want a host for the web app | 13 | Tom, Patryk, Fraser | [6 empty] | Used Microsoft Azure w/ Eclipse
Research different methods for hosting | 2 | Everyone | Done | 2
Choose host method (which software to use) | 0.5 | Everyone | Done | 0.5 |  |  |  |  | Resolved w/ Microsoft Azure
Set up project using host method | 8 | Tom, Patryk, Fraser | Done |  | 6 | 4 |  |  | Original project format was outdated, so had to be changed
Link to Github | 1 | Everyone | Done |  | 1
Connect web app to database | 2 | Patryk, Fraser, Tom | Done |  | 4 | 1 | 3 | 2 | Connection worked when running from java file, couldnt find driver when run via jsp file. Its taking longer than excepted
As a client, I want a website to act as a front end for my web app | 13 | Fraser, Josh, Aditya, Patryk
Research how to integrate Java onto website | 2 | Fraser | Done | 2
Design CSS stylesheet | 0.5 | Fraser, Josh | Done |  |  |  | 2 | 1 | Originally looked at templates, but decided to make our own
Design basic framework for the website | 1 | Josh | Done |  | 0.5 | 0.5
Create input form | 2 | Aditya, Josh | Done | 3 | 2.5 | 3 |  |  | #
Create display table | 2 | Patryk | Done |  |  | 2
Create general layout | 3 | Aditya, Josh | Done | 3 | 3.5 | 4.5 |  |  | #
As a user, I can search for institutions which provide a procedure | 1 | Patryk, Tom
Implement search function based on Procedure code | 0.5 |  | Done |  |  |  |  | 0.5
Implement search function based on condition description | 0.5 |  | Done |  |  |  |  | 0.5
Implement search function based on price range | 0.5 |  | Done |  |  |  |  | 0.5 | Item was added Friday morning, since we had some spare time
As a client, I want a database to store our dataset | 8 | Michael
Set up database | 1 | Michael | Done | 1 | 0.5
Get dataset | 0.5 | Michael | Done | 0.5
Clean dataset | 0.5 | Michael | Done |  | 0.5
Design table structure | 1 | Michael | Done | 1
Design relationships | 1 | Michael | Done | 0.5 | 0.5
Import dataset | 0.5 | Michael | Done | 0.5
Create procedures | 0.5 | Michael | Done |  |  | 0.5 | 1 |  | Taking Longer than expected
Create view | 1 | Michael | Done |  |  | 0.5
Set up an access/authentication system. | 2 | Michael | Done |  |  | 1 |  |  | Didn't take as long as expected