## Sheet1
Product Backlog Story | Original Estiamate of Story Points | Assigned To | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | General Notes
As a user, I can view search results on a map | 10
Research libraries/plugins | 2 | Aditya | In progress
Convert address to coordinates | 3 | Aditya | Not started
Display search results on map | 5 | Aditya, Tom | Not started
As a user, I want to search results by distance | 4
Calculate distance between two points | 3 | Michael | Not started
Sort search results by distance | 1 | Patryk | Not started
As a user, I can sort results using a custom ranking | 5
Determine how ranking is calculated | 2 | Tom | In progress
Determine weighting of price and distance | 2 | Tom | Not started
Implement algorithm | 1 | Tom | Not started
As a user, I want a more user friendly website | 8
Update design to be more user friendly | 3 | Josh | In progress
Create a new page for search results | 2 | Josh | Not started
Conform to WCAG accessibility standards | 3 | Josh | Not started
As an administrator, I want to log in to the website | 3
Create login page | 1 | Fraser | In progress
Add login details to database | 1 | Michael | Not started
Implement login validation | 1 | Fraser | Not started
As an administrator, I want to update the database | 10
Create admin page | 5 | Fraser,Patryk | In progress
Create stored procedures | 3 | Michael | Not started
Implement method to access stored procedures from website | 2 | Fraser,Patryk | Not started