## Sheet1
Product Backlog Story | Original Estiamate of Story Points | Assigned To | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | General Notes
As a user, I can view search results on a map | 10
Research libraries/plugins | 2 | Aditya | Done | 1 | 1
Convert address to coordinates | 3 | Tom | Done |  |  | 3
Display map | 2 | Aditya | Done | 2 | 3 | 1 | 2 | 2
Display search results on map | 3 | Aditya, Tom | Done |  |  |  | 3
As a user, I want to search results by distance | 4
Calculate distance between two points | 3 | Michael | Not started
Sort search results by distance | 1 | Patryk | Done |  |  |  |  | 1
As a user, I can sort results using a custom ranking | 5
Determine how ranking is calculated | 2 | Tom | Done |  | 1
Determine weighting of price and distance | 2 | Tom | Done |  | 2
Implement algorithm | 1 | Tom | Done |  | 2
As a user, I want a more user friendly website | 8
Update design to be more user friendly | 3 | Josh | In progress |  | 1
Create a new page for search results | 2 | Josh | In progress |  | 1
Conform to WCAG accessibility standards | 3 | Josh | Not started
As an administrator, I want to log in to the website | 5
Create login page | 1 | Fraser | Done |  | 1
Add login details to database | 1 | Michael | Done |  |  | 1
Implement login validation | 2 | Fraser | Done |  |  | 1 | 1
Add redirection to other pages | 1 | Fraser | Done |  |  |  | 1
As an administrator, I want to update the database | 10
Create admin page | 2 | Fraser,Patryk | Done |  | 1 |  | 1
Add upload function | 1 | Patryk | Done |  | 3
Create stored procedures | 2 | Michael | Done |  |  | 1 | 1
Clean uploaded data | 3 | Patryk | Done |  | 3 |  | 2
Update database algorithm | 2 | Patryk | Done |  |  |  | 2
Integrate login page & procedure page | 2 | Fraser,Patryk | Done |  |  |  |  | 2
Total story points to complete - | 42 |  | Points completed per day | 3 | 19 | 7 | 13 | 5