## Sheet1
Section | User Story | Priority | Complexity
Website - Developer | As a client, I want a host for the web app | 10 | 13
| As a client, I want my web app to meet WCAG accessibility standards | 3 | 3
| As a client, I want a website to act as a front end for my web app | 10 | 13
Website - User | As a user, I can search for institutions which provide a procedure | 9 | 1
| As a user, I can view search results on a map | 8 | 1
| As a user, I can sort results by price | 7 | 1
| As a user, I can sort results by distance from current location | 7 | 1
| As a user, I can sort results by distance from a selected location | 7 | 1
| As a user, I can restrict a search by entering a price range | 7 | 1
| As a user, I can sort results using a custom ranking algorithm | 5 | 2
Database | As a client, I want a database to store our dataset | 10 | 5
| As a client, I want to be able to update the database | 5 | 2
Website - Admin | As an administrator, I can log in to the website | 5 | 3
| As an administrator, I can access the database from the website | 5 | 5
52