## Sheet1
Product Backlog Story | Story Points | Assigned To | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | General Notes
As a client, I want a host for the web app | 13 | Tom, Patryk, Fraser | [6 empty] | Used Microsoft Azure w/ Eclipse
Research different methods for hosting | 2 | Everyone | Done | 2
Choose host method (which software to use) | 0.5 | Everyone | Done | 0.5 |  |  |  |  | Resolved w/ Microsoft Azure
Set up project using host method | 8 | Tom, Patryk, Fraser | Done |  | 6 | 4
Link to Github | 1 | Everyone | Done |  | 1
Connect web app to database | 2 | Patryk, Fraser, Tom | In progress |  | 4 | 1 | 3 |  | Connection worked when running from java file, couldnt find driver when run via jsp file. Its taking longer than excepted
As a client, I want a website to act as a front end for my web app | 13 | Fraser, Josh,Aditya
Research how to integrate Java onto website | 2 | Fraser | Done | 2 | 0
Select a template for CSS. | 0.5 | Fraser, Josh | In progress | 0
Design basic framework for the website | 1 | Josh | Done | 0 | 0.5 | 0.5
Create input form | 2 | Aditya, Josh | Done | 3 | 2.5 | 3
Create display table | 2 | Patryk | Done | 0 | 0 | 2
Create general layout | 3 | Aditya, Josh | Done | 3 | 3.5 | 4.5
As a user, I can search for institutions which provide a procedure | 1 | Patryk, Tom
Implement search function based on Procedure code | 0.5 |  | In progress |  |  |  | 3 |  | Problem getting it to work when deployed as web app, app cant find driver to conenct to database
Implement search function based on condition description | 0.5 |  | In progress |  |  |  | 3
As a client, I want a database to store our dataset | 8 | Michael
Set up database | 1 | Michael | Done | 1 | 0.5
Get dataset | 0.5 | Michael | Done | 0.5
Clean dataset | 0.5 | Michael | Done |  | 0.5
Design table structure | 1 | Michael | Done | 1
Design relationships | 1 | Michael | Done | 0.5 | 0.5
Import dataset | 0.5 | Michael | Done | 0.5
Create procedures | 0.5 | Michael | In progress |  |  | 0.5 | 1 |  | Taking Longer than expected
Create view | 1 | Michael | Done |  |  | 0.5
Set up an access/authentication system. | 2 | Michael | Done |  |  | 1 |  |  | Didn't take as long as expected